## Version 1
Risk Register for UOW Event Booking System
Version 1
Project Name: |  | UOW Event Booking System
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 |  | Miscommunication between members | People risk | Be concise and clear in every meetings Taking down notes. | Amirah | Medium | High | Nil
2 |  | Cannot finish within the schedule | Schedule Risk | Close monitoring on the activities and make changes if required | Zhi Kai | Medium | High | Some additional features may not be added to our program as planned
3 |  | Not clear with the project scope | Scope Risk | Clarify with CIO | Zhi Kai | Medium | High | Nil
4 |  | Conflict within team members | People risk | Spend more time to understand each other | Zhi Kai | Medium | Medium | Nil
5 |  | Members not attending meetings | People risk | Plan meetings earlier, use video calls if neccessary or use meeting minutes to notify those that were not present for the meetings to be updated with the latest information | Zhi Kai | Medium | Medium | Nil
6 |  | Team members withdrawing from the course | People risk | Have backup for every roles | Zhi Kai | Low | Low | The backup may require some time to adapt
7 |  | Team members are from different countries, thus may have different work cultures | Culture Risk | Get to know each other more with more plans for activities | Amirah | Low | Low | May not be able to fully adapt/understand within a short amount of time

## Version 2
Risk Register for UOW Event Booking System
Version 2
Project Name: |  | UOW Event Booking System
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 |  | Missing out some of the programming functionalities to test on | Technology Risk | Closely monitor and review the test script and test data covers all functionalities of the program that has to be tested | Zhi Kai, Amirah | Medium | High | Nil
2 |  | Corrupted software/data | Technology Risk | Ensure there are additional latest backup after each progress | Zhi Kai, Mingyao | Medium | High | Nil
3 |  | Insufficient budget for future project plans | Scope Risk | Closely monitor the budget spent, propose new update budget plans to CIO if it happens | Zhi Kai | Medium | High | Nil
4 |  | Team not strong in programming | Technology Risk | Provide guidance and assign easier tasks to members who are weaker in certain areas | Li Shan | Medium | High | Takes time to fully understand a programming language
5 |  | Program may turns out to be different from what was planned initially | Scope Risk | Constant reporting of the phases of programming stages to the team | Ming Yao | Medium | High | Nil
6 |  | Miscommunication between members | People risk | Be concise and clear in every meetings Taking down notes. | Amirah | Medium | High | Nil
7 |  | Unable to deliver program within stipulated time | Schedule Risk | Close monitoring on the activities and make changes if required | Zhi Kai | Medium | High | Some additional features may not be added to our program as planned
8 |  | Not clear with the project scope | Scope Risk | Clarify with CIO | Zhi Kai | Medium | High | Nil
9 |  | Conflict within team members | People risk | Spend more time to understand each other | Zhi Kai | Medium | Medium | Nil
10 |  | Members not attending meetings | People risk | Plan meetings earlier, use video calls if neccessary or use meeting minutes to notify those that were not present for the meetings to be updated with the latest information | Zhi Kai | Medium | Medium | Nil
11 |  | Team members withdrawing from the course | People risk | Have people to backup for every roles and understand what they do | Zhi Kai | Low | Low | Nil
12 |  | Team members are from different countries, thus may have different work cultures | Culture Risk | Get to know each other more with more plans for activities | Amirah | Low | Low | Nil

## Version 3
Risk Register for UOW Event Booking System
Version 3
Project Name: |  | UOW Event Booking System
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 |  | Missing out additional features required from the project change | Technology Risk | Closely monitor and review the test script and test data covers all functionalities of the program that has to be tested | Zhi Kai, Amirah | Medium | High | Nil
2 |  | Corrupted software/data | Technology Risk | Ensure there are additional latest backup after each progress | Zhi Kai, Mingyao | Medium | High | Nil
3 |  | Program not able to meet new required changes | Scope Risk | Constant Review from team and make prompt changes when required | Ming Yao | Medium | High | Program may still not be able to meet expectation
4 |  | Miscommunication between members | People risk | Be concise and clear in every meetings Taking down notes. | Amirah | Medium | High | Nil
5 |  | Unable to deliver new changes that program requires within schedule | Schedule Risk | Include longer working hours when required | Zhi Kai | Medium | High | Nil
6 |  | Unsure of the project scope due to new changes | Scope Risk | Clarify with CIO | Zhi Kai | Medium | High | Nil
7 |  | Members not attending meetings | People risk | Plan meetings earlier, use video calls if neccessary or use meeting minutes to notify those that were not present for the meetings to be updated with the latest information | Zhi Kai | Medium | Medium | Nil
8 |  | Team members withdrawing from the course | People risk | Have people to backup for every roles and understand what they do | Zhi Kai | Low | Low | Nil
9 |  | Team members are from different countries, thus may have different work cultures | Culture Risk | Get to know each other more with more plans for activities | Amirah | Low | Low | Nil