## Sheet1
Project Name: | UOW Event Booking System
Test CaseID: | STA-01
Test Case Description: | Check function of Staff Account
Created By: | Amirah
Tested On: | 2019-11-04
Pre-Condition: | Open laptop & launch the program
Test Step | Test Description | Test Data / Step | Expected Results | Actual Results | Pass/ Fail | Remarks | Screenshot if fail
STA-01-1 | Launch the program |  | UOW Booking System's login page should appear | UOW Booking System's login page appeared | Pass
STA-01-2-1 | Unsuccessful login - Empty cell in Login ID / password | Click on 'Login' button | A pop up message would appear warning user that the fields are not filled up | Pop up message appeared | Pass
STA-01-2-2 | Unsuccessful login - Wrong details entered | Login ID: 1903903 Password: wrong Click 'Login' button | A pop up message would appear to let the user know the ID / password is wrong | Pop up message appeared | Pass
STA-01-2-3 | Successful login | Login ID: 1345642 Password: zxcasd | Upon successful login, it will direct to the STAFF main page | Directed to STAFF main page | Pass
STA-01-3-1 | To create new events | Fill in all details required in the page. | All the written details can be able typed in their respective boxes | Details can be entered in the boxes | Pass
STA-01-3-2 | Successful creation of events - all details added in the boxes provided | Click on 'Create' button | A pop up message would appear to let the user know that the event is saved/created and the event details will be added in the table under 'Event List' | A pop up message appeared and the events are added into the table 'Event List' | Pass
STA-01-3-3 | Unsuccessful creation of events - no details added in the boxes | Click on 'Create' button | A pop up message would appear to warn the users that one or more details are empty | Pop up message appeared | Pass
STA-01-4-1 | To edit the event details on the table | Click on the event that the user wants to edit | User should be able to change any of the details except for the public/private column and the ticket booked column | User can change any the details except for the public/private column and the ticket booked column | Pass
STA-01-4-2 | Confirm the changes made to the table | Click on 'edit' button | A pop up message would appear that tells the user that they already updated the event details | A pop up message appeared | Pass
STA-01-5-1 | To delete event created on the table | Select the event from table that the user wants to delete | Selected event will be highlighted in the table | Selected event highlighted in the table | Pass
STA-01-5-2 | Check the delete button function | Click 'delete' button after adding all the details | A pop message should appear to let the users know that the event Is already deleted and the frame will redirect back to the STAFF main page | A pop message appeared and directed back to STAFF main page | Pass
STA-01-6-1 | Check the account button function to change the user's password | Click 'account' button | Frame will direct to the 'Account Management' page | Frame redirected to the account management page | Pass
STA-01-6-2 | To change the password | Typed in the new password that the user wanted to change. Then click 'Save' button | The NEW password should be able to changed | NEW password can be changed | Pass
STA-01-7 | Log out of Staff Account | Click 'Logout' button | STAFF main page will be closed and login page will appear | STAFF main page closed and login page appeared | Pass
STA-01-8 | To exit the program | Click on 'x' button | The program should terminate and the frame should close | Frame closed | Pass