## Sheet1
Project Name: | UOW Event Booking System
Test CaseID: | SU-01
Test Case Description: | Check function of Super User Account
Created By: | Amirah, Arr Lay
Checked By : | Li Shan
Tested On: | 2019-11-06
Pre-Condition: | Open laptop to launch the program
Test Step | Test Description | Test Data / Step | Expected Results | Actual Result | Pass/Fail | Remarks | Screenshot if fail
SU-01-1 | Launch the program |  | UOW Booking System should launch and login page will appear | UOW Booking System can be launched and login page appeared | Pass
SU-01-2-1 | Unsuccessful login - Empty Cell in Login ID / Password | Click on 'Login' button | A pop up message would appear warning user that the fields are not filled up | Pop up message appeared | Pass
SU-01-2-2 | Unsuccessful login - Wrong Details Entered | Login ID = 9111111 Password = abcde Click on 'Login' Button | A pop up message would appear warning user that the ID / Password is incorrect | Pop up message appeared | Pass
SU-01-2-3 | Successful Login | Login ID = 9111111 Password = Super999 Click 'Login' Button | Login success, the frame will direct to the SUPER USER main page | Directed to main page | Pass
SU-01-3-1 | View event details and status |  | List of event should appear in the event listing table | Events are shown in the table | Pass
SU-01-3-2 | Approve a pending event | Select the event then click on the 'Approve Event' button | Upon selecting an event with pending status, 'Approve Event' button would be enabled. After pressing on the button, a pop up message would appear indicating that the event is successfully booked. The status of the event would then change to approve | Pop up message appeared and status successfully changed to approve | Pass
SU-01-4-1 | Access Check Venue Availabilty function | Click on 'Check Venue Availabilty' | The frame would extend with various textbox for user to enter the venue, start date and end date | The frame extended and the textboxes appeared | Pass
SU-01-4-2 | Check Venue Availabilty | Venue = Auditorium Start Date = 01112019 End Date = 30112019 Click 'Confirm' button | Events using the venue during the respective date would appear in the table below | Events are shown in the table | Pass
SU-01-5 | Log out of Super User account | Click 'Logout' button | Super User frame should close and login page should appear | Frame closed, login page appear | Pass
SU-01-6 | Exit the program | Click on 'x' button | The program should terminate and the frame should close | Frame closed | Pass